## Baseline_Schedule
Activity_ID | Activity_Name | Planned_Start | Planned_Finish | Budgeted_Cost | Dependency
CONFIG | TOTAL_CONTRACT_VALUE |  |  | 240100.82
CONFIG | PROJECT_START_DATE | 2025-01-15
CONFIG | PROJECT_END_DATE |  | 2025-06-30
1 | Site Survey & Mobilization | 2025-01-15 | 2025-01-20 | 15000 | 0
2 | Civil Works - Trenching | 2025-01-21 | 2025-02-15 | 45000 | 1
3 | Fibre Cable Laying | 2025-02-01 | 2025-03-15 | 60000 | 2
4 | Fibre Splicing | 2025-03-16 | 2025-04-15 | 35000 | 3
5 | Testing & Commissioning | 2025-04-16 | 2025-05-15 | 25000 | 4
6 | Site Restoration & Handover | 2025-05-16 | 2025-06-15 | 20000 | 5

## Activity_Log
Log_Date | Activity_ID | Event_Type
2025-01-15 | 1 | STARTED
2025-01-19 | 1 | FINISHED
2025-01-21 | 2 | STARTED
2025-02-18 | 2 | FINISHED
2025-02-05 | 3 | STARTED

## Expenditure_Log
Spend_Date | Activity_ID | Category | Description | Reference_ID | Amount
2025-01-17 | 1 | Labour | Survey team wages | INV-001 | 8500
2025-01-18 | 1 | Vehicle | Site transport | VEH-010 | 2500
2025-01-25 | 2 | Labour | Trenching crew - Week 1 | INV-005 | 12000
2025-02-01 | 2 | Labour | Trenching crew - Week 2 | INV-008 | 11500
2025-02-05 | 2 | Material | Ducting pipes | PO-101 | 18000
2025-02-10 | 3 | Material | Fibre cable - 500m | PO-115 | 25000
2025-02-15 | 2 | Vehicle | Excavator rental | VEH-022 | 4500
2025-02-20 | 3 | Labour | Cable laying team | INV-012 | 9500