## Project_Schedule
PROJECT STATUS DASHBOARD - DATA ENTRY FORM
REPORTING PERIOD: | 2026/02
PROJECT NAME: |  | Liberty Tower Fibre Relocation |  | TOTAL BUDGET: | 240100.82
PROJECT NUMBER: |  | IN963051 |  | START DATE: | 2025-01-15
CLIENT: |  | Liberty Properties |  | TARGET END DATE: | 2025-06-30
PROJECT MANAGER: |  | J. Smith |  | STATUS: | In Progress
PROJECT SCHEDULE (BASELINE PLAN)
Activity ID | Activity Name | Planned Start | Planned End | Budgeted Cost (R) | Depends On | Actual Start | Actual End
1 | Site Survey & Mobilization | 2025-01-15 | 2025-01-20 | 15000 | - | 2025-01-15 | 2025-01-19
2 | Civil Works - Trenching | 2025-01-21 | 2025-02-15 | 45000 | 1 | 2025-01-21 | 2025-02-18
3 | Fibre Cable Laying | 2025-02-01 | 2025-03-15 | 60000 | 2 | 2025-02-05
4 | Fibre Splicing | 2025-03-16 | 2025-04-15 | 35000 | 3
5 | Testing & Commissioning | 2025-04-16 | 2025-05-15 | 25000 | 4
6 | Site Restoration & Handover | 2025-05-16 | 2025-06-15 | 20000 | 5

## Expenditure_Log
EXPENDITURE LOG
Record every payment made. Attach invoice/PO reference.
Date | Activity ID | Category | Description | Reference (Invoice/PO) | Amount (R)
2025-01-17 | 1 | Labour | Survey team wages | INV-001 | 8500
2025-01-18 | 1 | Vehicle | Site transport | VEH-010 | 2500
2025-01-25 | 2 | Labour | Trenching crew - Week 1 | INV-005 | 12000
2025-02-01 | 2 | Labour | Trenching crew - Week 2 | INV-008 | 11500
2025-02-05 | 2 | Material | Ducting pipes | PO-101 | 18000
2025-02-10 | 3 | Material | Fibre cable - 500m | PO-115 | 25000
2025-02-15 | 2 | Vehicle | Excavator rental | VEH-022 | 4500
2025-02-20 | 3 | Labour | Cable laying team | INV-012 | 9500

## Risk_Register
RISK & ISSUES REGISTER
Date Identified | Risk/Issue Description | Impact (H/M/L) | Status | Mitigation Action
2025-01-22 | Trenching delayed due to unexpected rock | H | Resolved | Rented rock breaker
2025-02-10 | Material delivery delayed by supplier | M | Open | Escalated to procurement